## Excel data (hide) (hidden)
ALL DATA ON THIS SHEET IS REQUIRED FOR FUNCTIONALITY OF THE TRACKER WORKBOOK. CHANGES MADE HERE WILL BE REFLECTED IN THE REST OF THE TRACKER.
[7 empty] | Excel data (hide) | Cover - Project Details | Exemplar | Part 2-Reg 4 | Part 2-Reg 6 | Part 2-Regs 7-8 | Part 6-Regs 22-28 | Part 7-Reg 36 | Part 9-Regs 41-44 | Part 9A-Reg 44ZC-44A | Part 9B-Reg 44D-44I | Regulations | Sch.1-Part A | Sch.1-Part B | Sch.1-Part C | Sch.1-Part D | Sch.1-Part E | Sch.1-Part F | Sch.1-Part G | Sch.1-Part H | Sch.1-Part J | Sch.1-Part K | Sch.1-Part L | Sch.1-Part M | Sch.1-Part O | Sch.1-Part P | Sch.1-Part Q | Sch.1-Part R | Sch.1-Part S | Sch.1-Part T
Responsible Party | Responsible | Route to compliance | Status | WorkStage | YesorNo | Status
Access Consultant | Access | Approved Document guidance | Not started | Stage 2 Concept Design | Yes | Not started |  |  |  | 7 | 17 | 6 | 7 | 1 | 4 | 10 | 27 | 79 | 4 | 11 | 7 | 1 | 4 | 2 | 16 | 14 | 7 | 12 | 4 | 6 | 3 | 1 | 1 | 6 | 7 | 1
Acoustic Consultant | Acoustic | ISO/EN/BS guidance | Design in progress | Stage 3 Spatial Design | No | Design in progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Architect | Architect | Eurocode guidance | Ready for submission | Stage 4 Technical Design |  | Ready for submission |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil Engineer | Civils | Engineered solution | Submitted for approval |  |  | Submitted for approval |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Façade Consultant | Façade | Performance certified solution | Granted conditional approval |  |  | Granted conditional approval |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fire Engineer | Fire |  | Granted approval |  |  | Granted approval |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interior Designer | Interior |  | Not relevant |  |  | Not relevant |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landscape Architect | L'scape | [5 empty] | Sheets
Mechanical & Electrical Engineer | MEP | [5 empty] | Excel data (hide) | Go To Sheet
Structural Engineer | Structure | [5 empty] | Cover - Project Details | Go To Sheet
Specialist Contractor | Contractor | [5 empty] | Exemplar | Go To Sheet
Client | Client | [5 empty] | Part 2-Reg 4 | Go To Sheet
[7 empty] | Part 2-Reg 6 | Go To Sheet
[7 empty] | Part 2-Regs 7-8 | Go To Sheet
[7 empty] | Part 6-Regs 22-28 | Go To Sheet
[7 empty] | Part 7-Reg 36 | Go To Sheet
[7 empty] | Part 9-Regs 41-44 | Go To Sheet
[7 empty] | Part 9A-Reg 44ZC-44A | Go To Sheet
| IF YOU WISH TO ADD TO THE LIST ABOVE - 5 ADDITIONAL BLANK SLOTS HAVE BEEN PROVIDED. | [5 empty] | Part 9B-Reg 44D-44I | Go To Sheet
[7 empty] | Sch.1-Part A | Go To Sheet
[7 empty] | Sch.1-Part B | Go To Sheet
[7 empty] | Sch.1-Part C | Go To Sheet
[7 empty] | Sch.1-Part D | Go To Sheet
[7 empty] | Sch.1-Part E | Go To Sheet
[7 empty] | Sch.1-Part F | Go To Sheet
[7 empty] | Sch.1-Part G | Go To Sheet
[7 empty] | Sch.1-Part H | Go To Sheet
[7 empty] | Sch.1-Part J | Go To Sheet
[7 empty] | Sch.1-Part K | Go To Sheet
[7 empty] | Sch.1-Part L | Go To Sheet
[7 empty] | Sch.1-Part M | Go To Sheet
[7 empty] | Sch.1-Part O | Go To Sheet
[7 empty] | Sch.1-Part P | Go To Sheet
[7 empty] | Sch.1-Part Q | Go To Sheet
[7 empty] | Sch.1-Part R | Go To Sheet
[7 empty] | Sch.1-Part S | Go To Sheet
[7 empty] | Sch.1-Part T | Go To Sheet

## Cover - Project Details
Project Team
Dutyholders: | Organisation | Key Contact Name | Key Contact Email | Submission Status Summary
Client: | Company Name | Name | Email | Graphs reflect the progress of each line item of the tracker. All items should ultimately be either dark green (granted approval) or grey (not relevant)
Principal Designer (BRPD): | Company Name | Name | Email
Principal Contractor (BRPC): | Company Name | Name | Email
Designers | Organisation | Key Contact Name | Key Contact Email
Access Consultant (ACC) | Company Name | Name | Email
Acoustic Consultant (ACO) | Company Name
Architect (A) | Company Name
Civil Engineer (CE) | Company Name
Façade Consultant (FC) | Company Name
Fire Engineer (FE) | Company Name
Interior Designer (ID) | Company Name
Landscape Architect (LA) | Company Name
Mechanical & Electrical Engineer (ME) | Company Name
Structural Engineer (SE) | Company Name
Specialist Contractor (SC) | Company Name
Submission Status
Not started | Not started
Design in progress | Design in progress
Ready for submission | Ready for submission
Submitted for approval | Submitted for approval
Granted conditional approval | Granted conditional approval
Granted approval | Granted approval
Relevance of requirement or regulation
Shade green if relevant to project | Relevant
Shade grey if not relevant | Not relevant
This tracker is for the use of the building regulations principal designer (BRPD) to assist in planning, managing and monitoring the design of the building in compliance with the relevant requirements of the Building Regulations.
In the coordination and completion of this tracker, the building regulations principal designer (BRPD) shall seek the advice of the designers and/or the building regulations principal contractor and shall be entitled to rely on such advice (for the avoidance of doubt, including advice on whether the design is being executed in accordance with the building regulations) which the other designers and/or building regulations principal contractor provide to the BRPD.
The BRPD shall not be responsible for verifying the accuracy or completeness of such advice and/or design and shall not be deemed under any circumstances to have assumed responsibility for or to have warranted the accuracy or completeness of the same.
The BRPD shall have no liability or responsibility for the design or fitness for purpose of the design, the specification or choice of materials used in the construction of the Works, and/or the inspection, acceptance and approvals given or made in relation to the design and construction of the Works.
Version 2024.08 - Formatting updated

## Part 2-Reg 4
Building Regulations Part 2 Control of Building Work
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting relevant requirement
Ref | Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
Regulation 4. - Requirements relating to building work
R4 | Regulation 4. - (1) | (1) Subject to paragraph (2) building work shall be carried out so that— (a)it complies with the applicable requirements contained in Schedule 1; and (b)in complying with any such requirement there is no failure to comply with any other such requirement, except as may be provided for in paragraphs (1C) and (1D)]. | [8 empty] | Not started
|  | (1A) The applicable requirements contained in Schedule 1 are— (a)the applicable requirements contained in Schedule 1 that apply in all cases, subject to paragraph (1C); and (b)any applicable requirement contained in Schedule 1, and described in the first column of that Schedule as an optional requirement, that applies in relation to the building work in question by virtue of paragraphs (1B), (1C) and (1D). | [8 empty] | Not started
|  | (1B) An optional requirement as described in paragraph (1A)(b) shall apply to building work in any case where the planning permission under which the building work is carried out— (a)specifies that optional requirement by reference to these Regulations; and (b)makes it a condition that the requirement must be complied with. | [8 empty] | Not started
|  | (1C) An optional requirement shall apply in substitution for a requirement of Schedule 1 to the extent that the terms of the optional requirement in the second column of Schedule 1 so provide. | [8 empty] | Not started
|  | (1D) An optional requirement shall apply, and another optional requirement shall not apply, to the extent that the terms of the first-mentioned optional requirement in the second column of Schedule 1 so provide. | [8 empty] | Not started
R4 | Regulation 4. - (2) | (2) Where— (a)building work is of a kind described in regulation 3(1)(g), (h) or (i); and (b)the carrying out of that work does not constitute a material alteration, that work need only comply with the applicable requirements of Part L of Schedule 1 (in addition to the requirements of regulation 7) | [8 empty] | Not started
R4 | Regulation 4. - (3) | (3) Building work shall be carried out so that, after it has been completed— (a)any building which is extended or to which a material alteration is made; or (b)any building in, or in connection with, which a controlled service or fitting is provided, extended or materially altered; or (c)any controlled service or fitting, complies with the applicable requirements of Schedule 1 or, where it did not comply with any such requirement, is no more unsatisfactory in relation to that requirement than before the work was carried out. F7[F8(4) This paragraph applies in relation to a building where— (a)building work is undertaken in respect of that building (“relevant work”); and (b)Part L of Schedule 1 imposes a requirement in respect of the relevant work. (5) Notwithstanding paragraph (3), upon completion of the relevant work, any building to which paragraph (4) applies must— (a)comply with Part F of Schedule 1; or (b)where the building did not comply with Part F of Schedule 1 before the relevant work was begun, be no more unsatisfactory in relation to it than before the work was begun. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Part 2-Reg 6
Building Regulations Part 2 Control of Building Work
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting relevant requirement
Ref | Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
Regulation 6. - Requirements relating to material change of use
R6 | Regulation 6. - (1) | 6.—(1) Where there is a material change of use of the whole of a building, such work, if any, shall be carried out as is necessary to ensure that the building complies with the applicable requirements of the following paragraphs of Schedule 1— (a)in all cases, B1 (means of warning and escape) B2 (internal fire spread—linings) B3 (internal fire spread—structure) B4(2) (external fire spread—roofs) B5 (access and facilities for the fire service) C2(c) (interstitial and surface condensation) F1 (ventilation) G1 (cold water supply) G3(1) to (3) (hot water supply and systems) G4 (sanitary conveniences and washing facilities) G5 (bathrooms) G6 (kitchens and food preparation areas) H1 (foul water drainage) H6 (solid waste storage) J1 to J4 (combustion appliances) L1 (conservation of fuel and power) P1 (electrical safety); S2 (infrastructure for the charging of electric vehicles) T Toilet accomodation (from Oct 2024) | [8 empty] | Not started
|  | (b)in the case of a material change of use described in regulation 5(c), (d), (e) or (f), A1 to A3 (structure) | [8 empty] | Not started
|  | (c)in the case of a building exceeding [eleven] metres in height, B4(1) (external fire spread—walls); | [8 empty] | Not started
|  | (d)in the case of a material change of use described in regulation 5(a), (b), (c), (d), (g), (h), (i) or, where the material change provides new residential accommodation, (f), C1(2) (resistance to contaminants); | [8 empty] | Not started
|  | (e)in the case of a material change of use described in regulation 5(a), C2 (resistance to moisture); | [8 empty] | Not started
|  | (f)in the case of a material change of use described in regulation 5(a), (b), (c), (g), (h) or (i), E1 to E3 (resistance to the passage of sound); | [8 empty] | Not started
|  | (g)in the case of a material change of use described in regulation 5(e), where the public building consists of or contains a school, E4 (acoustic conditions in schools); | [8 empty] | Not started
|  | (h)in the case of a material change of use described in regulation 5(a) or (b), G2 (water efficiency) and G3(4) (hot water supply and systems: hot water supply to fixed baths); | [8 empty] | Not started
|  | (i)in the case of a material change of use described in regulation 5(c), (d), (e) or (j), M1 (access to and use of buildings other than dwellings); | [8 empty] | Not started
|  | (j)in the case of a material change of use described in regulation 5(a), (b) or (g), Q1 (security). | [8 empty] | Not started
R6 | Regulation 6.- (2) | (2) Where there is a material change of use of part only of a building, such work, if any, shall be carried out as is necessary to ensure that— (a)that part complies in all cases with any applicable requirements referred to in paragraph (1)(a); | [8 empty] | Not started
|  | (b)in a case in which sub-paragraphs (b), (e), (f), (g) or (h) of paragraph (1) apply, that part complies with the requirements referred to in the relevant sub-paragraph; | [8 empty] | Not started
|  | (c)in a case to which sub-paragraph (c) of paragraph (1) applies, the whole building complies with the requirement referred to in that sub-paragraph; | [8 empty] | Not started
|  | (d)in a case to which sub-paragraph (i) of paragraph (1) applies— (i)that part and any sanitary conveniences provided in or in connection with that part comply with the requirements referred to in that sub-paragraph; and (ii)the building complies with requirement M1(a) of Schedule 1 to the extent that reasonable provision is made to provide either suitable independent access to that part or suitable access through the building to that part; | [8 empty] | Not started
|  | (e)in a case to which subparagraph (j) applies in respect of a material change of use described in regulation 5(b) or (g), that part complies with the requirement referred to in that subparagraph. | [8 empty] | Not started
R6 | Regulation 6.- (3) | (3) Subject to paragraph (4), where there is a material change of use described in regulation 5(k), such work, if any, shall be carried out as is necessary to ensure that any external wall, or specified attachment, of the building only contains materials of European Classification A2-s1, d0 or A1 (classified in accordance with the reaction to fire classification). | [8 empty] | Not started
R6 | Regulation 6.-(4) | (4) Paragraph (3) does not apply to the items listed in regulation 7(3). | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Part 2-Regs 7-8
Building Regulations Part 2 Control of Building Work
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting relevant requirement
Ref | Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
Regulation 7. - Materials and workmanship
R7 | Regulation 7. - (1) | (1) Building work shall be carried out— (a)with adequate and proper materials which— (i)are appropriate for the circumstances in which they are used, (ii)are adequately mixed or prepared, and (iii)are applied, used or fixed so as adequately to perform the functions for which they are designed; and (b)in a workmanlike manner. | [8 empty] | Not started
R7 | Regulation 7. - (1A) | 1A) Building work shall be carried out so that relevant metal composite material does not become part of an external wall, or specified attachment, of any building. | [8 empty] | Not started
R7 | Regulation 7. - (2) | (2) Subject to paragraph (3), building work shall be carried out so that materials which become part of an external wall, or specified attachment, of a relevant building are of European Classification A2-s1, d0 or A1 (classified in accordance with the reaction to fire classification) | [8 empty] | Not started
R7 | Regulation 7. - (3) | (3) Paragraph (2) does not apply to— (a)cavity trays when used between two leaves of masonry; (b)any part of a roof (other than any part of a roof which falls within paragraph (iv) of regulation 2(6)) if that part is connected to an external wall; (c)door frames and doors; (d)electrical installations; (da)fibre optic cables; (e)insulation and water proofing materials used below ground level or up to 300mm above that level; (f)intumescent and fire stopping materials where the inclusion of the materials is necessary to meet the requirements of Part B of Schedule 1; (g)membranes; (h)seals, gaskets, fixings, sealants and backer rods; (ha)components associated with a solar shading device excluding components whose primary function is to provide shade or deflect sunlight such as the awning curtain or slats; (i)thermal break materials where the inclusion of the materials is necessary to meet the thermal bridging requirements of Part L of Schedule 1; (j)window frames and glass; or (k)materials which form the top horizontal floor layer of a balcony which are of European Classification A1fl or A2fl-s1 (classified in accordance with the reaction to fire classification) provided that the entire layer has an imperforate substrate under it | [8 empty] | Not started
R7 | Regulation 7. - (4) | (4) In this regulation— (a)a “relevant building” means a building with a storey (not including roof-top plant areas or any storey consisting exclusively of plant rooms) at least 18 metres above ground level and which— (i)contains one or more dwellings; (ii)contains an institution; or (iii)contains a room for residential purposes; and (b)“above ground level” in relation to a storey means above ground level when measured from the lowest ground level adjoining the outside of a building to the top of the floor surface of the storey. | [8 empty] | Not started
Regulation 8. - Limitation on requirements
R8 | Regulation 8. | 8. Parts A to D, F to K, , N and P (except for paragraphs G2, H2 and J7) of Schedule 1 shall not require anything to be done except for the purpose of securing reasonable standards of health and safety for persons in or about buildings (and any others who may be affected by buildings, or matters connected with buildings). | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Part 6-Regs 22-28
Building Regulations Part 6 - Energy Efficiency Requirements
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting relevant requirement
Ref | Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
Regulation 22. - Requirements relating to a change to energy status
R22 | Regulation 22. | 22. Where there is a change to a building's energy status, such work, if any, shall be carried out as is necessary to ensure that the building complies with the applicable requirements of Part L of Schedule 1. | [8 empty] | Not started
Regulation 23. - Requirements for the renovation or replacement of thermal elements
R23 | Regulation 23.-(1) | 23 - (1) Where the renovation of an individual thermal element— (a)constitutes a major renovation; or (b)amounts to the renovation of more than 50% of the element’s surface area; the renovation must be carried out so as to ensure that the whole of the element complies with paragraph L1(a)(i) of Schedule 1, in so far as that is technically, functionally and economically feasible. | [8 empty] | Not started
| Regulation 23.-(2) | (2) Where the whole or any part of an individual thermal element is proposed to be replaced and the replacement— (a)constitutes a major renovation; or (b)(in the case of part replacement) amounts to the replacement of more than 50% of the thermal element’s surface area; the whole of the thermal element must be replaced so as to ensure that it complies with paragraph L1(a)(i) of Schedule 1, in so far as that is technically, functionally and economically feasible. | [8 empty] | Not started
Regulation 25B. - Nearly zero-energy requirements for new buildings
R25B | Regulation 25B. | 25B. Where a building is erected, it must be a nearly zero-energy building. | [8 empty] | Not started
Regulation 26. - CO² emission rates for new buildings
R26 | Regulation 26. | 26. Where a building is erected, it shall not exceed the target CO² emission rate for the building that has been approved pursuant to regulation 25, applying the methodology of calculation and expression of the energy performance of buildings approved pursuant to regulation 24 | [8 empty] | Not started
Regulation 26A. - Fabric energy efficiency rates
R26A | Regulation 26A. | 26A. Where a dwelling is erected, it shall not exceed the target fabric energy efficiency rate for the dwelling that has been approved pursuant to regulation 25, applying the methodology of calculation and expression of the energy performance of buildings approved pursuant to regulation 24. | [8 empty] | Not started
Regulation 28. - Consequential improvements to energy performance
R28 | Regulation 28. | 28.—(1) Paragraph (2) applies to an existing building with a total useful floor area over 1,000m2 where the proposed building work consists of or includes— (a)an extension; (b)the initial provision of any fixed building services; or (c)an increase to the installed capacity of any fixed building services. (2) Subject to paragraph (3), where this paragraph applies, such work, if any, shall be carried out as is necessary to ensure that the building complies with the requirements of Part L of Schedule 1. (3) Nothing in paragraph (2) requires work to be carried out if it is not technically, functionally and economically feasible. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Part 7-Reg 36
Building Regulations Part 7 - Water Efficiency
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting relevant requirement
Ref | Regulation | Functional Requirement Limits on application shown in italics. | Stage 2 Concept | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
Regulation 36. - Water efficiency of new dwellings
R36 | Regulation 36. | 36.—(1) The potential consumption of wholesome water by persons occupying a new dwelling must not exceed the requirement in paragraph (2). (2) The requirement referred to in paragraph (1) is either— (a)125 litres per person per day; or (b)in a case to which paragraph (3) applies, the optional requirement of 110 litres per person per day, as measured in either case in accordance with a methodology approved by the Secretary of State. (3) This paragraph applies where the planning permission under which the building work is carried out— (a)specifies the optional requirement in paragraph (2)(b); and (b)makes it a condition that that requirement must be complied with. (4) In this Part, “new dwelling” does not include a dwelling that is formed by a material change of use of a building within the meaning of regulation 5(g). | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Part 9-Regs 41-44
Building Regulations Part 9 - Testing and Commissioning
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting relevant requirement
Ref | Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
Regulation 41. - Sound insulation testing
R41 | Regulation 41.-(2) | 41 (2) Where this regulation applies, the person carrying out the work shall, for the purpose of ensuring compliance with paragraph El of Schedule 1— (a)ensure that appropriate sound insulation testing is carried out in accordance with a procedure approved by the Secretary of State; and (b)give a copy of the results of the testing referred to in sub-paragraph (a) to the local authority. | [8 empty] | Not started
Regulation 42. - Mechanical ventilation air flow rate testing
R42 | Regulation 42.-(2)(a) | 42.—(2) The person carrying out the work shall, for the purpose of ensuring compliance with paragraph (1) of Schedule 1— (a)ensure that testing of the mechanical ventilation air flow rate is carried out in accordance with a procedure approved by the Secretary of State; and (b)give notice of the results of the testing to the building control authority. | [8 empty] | Not started
Regulation 43. - Pressure testing
R43 | Regulation 43.-(2)(a) | 43.—(2) Where this regulation applies, the person carrying out the work shall, for the purpose of ensuring compliance with regulation 26 and regulation 26A and paragraph L1(a)(i) of Schedule 1— (a)ensure that— (i)pressure testing is carried out in such circumstances as are approved by the Secretary of State; and (ii)the testing is carried out in accordance with a procedure approved by the Secretary of State; and (b)subject to paragraph (5), give notice of the results of the testing to the local authority building control authority. | [8 empty] | Not started
Regulation 44ZA. - Commissioning in respect of a system for on-site electricity generation
R44ZA | Regulation 44ZA. | 44ZA.—(1) This regulation applies to building work in respect of a building in relation to which paragraph L2 of Schedule 1 imposes a requirement, but does not apply to the provision or extension of any system for on-site electricity generation where testing and adjustment is not possible. (2) Where this regulation applies the person carrying out the work must, for the purpose of ensuring compliance with paragraph L2 of Schedule 1, give to the building control authority a notice confirming that the system for on-site electricity generation has been commissioned. (3) The notice must be given— (a)in the case where the building work is higher-risk building work for which an application for a completion certificate is required, to the regulator with the application; (b)in any other case, to the building control authority— (i)not later than the date on which the notice required by regulation 16(4) is required to be given; or (ii)where that regulation does not apply, not more than 30 days after completion of the work. (4) Where the regulator is the building control authority by virtue of section 91ZB of the Act (the regulator: building control authority for other work), it must send a copy of each notice it receives under this regulation in relation to a building to the local authority for the area in which the building is situated. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Part 9A-Reg 44ZC-44A
Building Regulations Part 9A - Infrastructure for electronic communications
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting relevant requirement
Ref | Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
Regulation 44ZC. - Cases in which paragraph RA2 of Schedule 1 modified or excluded
R44ZC | Regulation 44ZC.-(1) | 44ZC.-(1) The requirement in paragraph RA2 of Schedule 1 has effect subject to paragraphs (2) to (4). | [8 empty] | Not started
| Regulation 44ZC.-(2) | (2) Where a person carrying out building work of the kind described in the second column of paragraph RA1 of Schedule 1 (“the developer”)— (a)is unable to secure the provision of a connection with a gigabit-capable public electronic communications network for a cost not exceeding the cost cap, but (b)is able to secure the provision of a connection with a high-speed public electronic communications network for such a cost, | [8 empty] | Not started
| Regulation 44ZC.-(2) | paragraph RA2 of Schedule 1 is to be read as requiring the provision of a connection with a high-speed public electronic communications network. (3) Where the developer— (a)is unable to secure the provision of a connection with a high-speed public electronic communications network for a cost not exceeding the cost cap, but (b)is able to secure the provision of a connection with a USO-standard public electronic communications network for such a cost, | [8 empty] | Not started
| Regulation 44ZC.-(4) | paragraph RA2 of Schedule 1 is to be read as requiring the provision of a connection with a USO-standard public electronic communications network. (4) Where the developer is unable to secure the provision of a connection with a USO-standard public electronic communications network for a cost not exceeding the cost cap, paragraph RA2 of Schedule 1 does not apply. | [8 empty] | Not started
| Regulation 44ZC.-(5) | (5) In paragraphs (2) to (4)— “high-speed public electronic communications network” means a public electronic communications network that is a high-speed electronic communications network;“USO-standard public electronic communications network” means a public electronic communications network that provides at least the minimum download speed for the time being specified by virtue of section 65(2B)(a) of the Communications Act 2003 in the universal service order (as defined by section 151(1) of that Act). | [8 empty] | Not started
| Regulation 44ZC.-(6) | (6) The developer is to be treated as being able to secure the provision of a connection mentioned in any of paragraphs (2) to (4) for a cost not exceeding the cost cap unless— (a)the developer has invited at least two suitable providers to make, before the end of the 30th day after the date of the invitation, an offer to provide a connection of the kind mentioned in the paragraph in question, and (b)none of those providers has before that time offered to provide that connection free of charge or at a cost not exceeding the cost cap. | [8 empty] | Not started
| Regulation 44ZC.-(7) | (7) The cost cap is £2,000 in respect of each dwelling. | [8 empty] | Not started
| Regulation 44ZC.-(8) | (8) In calculating the cost to the developer of securing the provision of a connection— (a)there is to be included value added tax; (b)there is to be excluded— (i)the cost to the developer of installing gigabit-ready physical infrastructure in accordance with paragraph RA1 of Schedule 1, (ii)administrative costs of the developer, and (iii)the cost to an end-user (as defined by section 151(1) of the Communications Act 2003) of the provision of a public electronic communications service. | [8 empty] | Not started
| Regulation 44ZC.-(9) | (9) In paragraph (6)(a) “suitable provider” means the provider of a public electronic communications network whom the developer reasonably considers to be likely to be able to provide the connection referred to. | [8 empty] | Not started
Regulation 44A. - Application of paragraph R1 of Schedule 1 to educational buildings, buildings of statutory undertakers and Crown buildings
R44A | Regulation 44A | 44A.—(1) The requirements of paragraph R1 (in-building physical infrastructure for high-speed electronic communications networks) of Schedule 1 apply (insofar as applicable to other buildings) also to— (a)educational buildings and buildings of statutory undertakers (notwithstanding section 4(1) of the Act); (b)Crown buildings; and (c)building work carried out or proposed to be carried out by Crown authorities. (2) In this regulation “educational buildings and buildings of statutory undertakers” means buildings that fall within paragraphs (a), (b) or (c) of section 4(1) of the Act. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Part 9B-Reg 44D-44I
Building Regulations Part 9B - Infrastructure for the charging of electric vehicles
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting relevant requirement
Ref | Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
Regulation 44D. - Application of paragraph S1 of Schedule 1 (the erection of new residential buildings)
R44D | Regulation 44D.-(1) | (1) The requirements of paragraph S1 of Schedule 1 apply in relation to the erection of a new residential building with associated parking as follows. | [8 empty] | Not started
| 44D (2) | (2) The number of electric vehicle charge points that must be installed is the maximum number of electric vehicle charge points that it is possible to install at an average sum of £3600 or less for the connection cost of each electric vehicle charge point connection (“the £3600 cap”). | [8 empty] | Not started
| 44D (3) | (3) If it is not possible to completely fulfil the requirements of paragraph S1(2) of Schedule 1 as a result of the operation of the £3600 cap, cable routes for electric vehicle charge points must be installed in the associated parking spaces that would otherwise be required to have electric vehicle charge points, but for the operation of the £3600 cap. | [8 empty] | Not started
| 44D (4) | (4) Where the new residential building has, or will have, associated parking that is situated within a covered car park— (a)if there are or will be any associated parking spaces situated in a position other than in a covered car park— (i)the requirements of paragraph S1 of Schedule 1 must first be applied in relation to those parking spaces; then (ii)if the number of associated parking spaces, which are situated in a position other than in a covered car park, is insufficient to completely fulfil the requirements of paragraph S1(2) of Schedule 1, cable routes for electric vehicle charge points must be installed in— (aa)the number of parking spaces in the covered car park which, when added to the number of associated parking spaces which are situated in a position other than in the covered car park, corresponds to the total number of dwellings with associated parking, where the total number of associated parking spaces is 10 or less; (bb)all the associated parking spaces in the covered car park, where the total number of associated parking spaces is both less than the number of dwellings with associated parking and 10 or less; and (cc)all the associated parking spaces in the covered car park, where the total number of associated parking spaces is more than 10; | [8 empty] | Not started
| 44D (5) | (b)if all the associated parking spaces are situated in a covered car park, cable routes for electric vehicle charge points must be installed— (i)where there are 10 or fewer parking spaces— (aa)in the number of associated parking spaces in the covered car park which corresponds to the total number of dwellings with associated parking; (bb)in all the parking spaces where there are fewer parking spaces than there are dwellings; (ii)in all the parking spaces in the covered car park, where there are more than 10 parking spaces. | [8 empty] | Not started
Regulation 44E. - Application of paragraph S2 of Schedule 1 (dwellings resulting from a material change of use)
R44E | Regulation 44E.-(1) | (1) The requirements of paragraph S2 of Schedule 1 apply to a building, or a part of a building, undergoing a material change of use to result in one or more dwellings as follows. | [8 empty] | Not started
| 44E (2) | (2) The requirements of paragraph S2 of Schedule 1 apply— (a)if— (i)the circumstances specified in regulation 5(a), (b) or (g) apply; and (ii)the material change of use involves building work being done which includes work being done to any of the following— (aa)to a car park that is located within the site boundary of the building, where the nature of the work is such that it would be reasonable to expect that work to include enabling the requirements of paragraph S2 of Schedule 1 to be fulfilled; (bb)the electrical infrastructure of a car park, where that car park is located within the site boundary of the building; (cc)the electrical infrastructure of the building, where a car park is located inside the building; (b)subject to paragraph (3), if an electric vehicle charge point for each dwelling resulting from a building, or a part of a building, undergoing a material change of use can be accommodated within the incoming electrical supply to the building without having to upgrade the capacity of the incoming electrical supply to the building; and (c)if the building is not one in relation to which paragraph (4) applies. | [8 empty] | Not started
| 44E (3) | (3) If paragraph (2)(a) and (c) applies, but electric vehicle charge points for some but not all of the dwellings resulting from a building, or a part of a building, undergoing a material change of use can be accommodated within the incoming electrical supply to that building— (a)the requirements of paragraph S2 of Schedule 1 apply in respect of the maximum number of electric vehicle charge points that can be accommodated within the incoming electrical supply; and (b)cable routes for electric vehicle charge points must be installed in the associated parking spaces that would otherwise have been required under paragraph S2 of Schedule 1 to have had electric vehicle charge points installed. | [8 empty] | Not started
| 44E (4) | (4) The requirements of paragraph S2 of Schedule 1 do not apply if a building, or a part of a building, is— (a)listed in accordance with section 1 of the Planning (Listed Buildings and Conservation Areas) Act 1990; (b)in a conservation area designated in accordance with section 69 of that Act; or (c)included in the schedule of monuments maintained under section 1 of the Ancient Monuments and Archaeological Areas Act 1979, where compliance with the requirements of paragraph S2 of Schedule 1 would unacceptably alter the building’s character or appearance. | [8 empty] | Not started
| 44E (5)(a) | (5) If the building, or a part of a building, undergoing a material change of use to result in one or more dwellings has, or will have, associated parking that is situated within a covered car park— (a)if there are or will be any associated parking spaces situated in a position other than in a covered car park— (i)the requirements of paragraph S2 of Schedule 1 must first be applied in relation to those associated parking spaces; then (ii)if the number of associated parking spaces, which are situated in a position other than in a covered car park, is insufficient to completely fulfil the requirements of paragraph S2 of Schedule 1, cable routes for electric vehicle charge points must be installed in— (aa)all the associated parking spaces in the covered car park, where the total number of parking spaces is less than the number of such dwellings with associated parking; or (bb)the number of associated parking spaces in the covered car park which, when added to the number of associated parking spaces which are situated in a position other than in a covered car park, corresponds to the total number of such dwellings with associated parking; | [8 empty] | Not started
| 44E (5)(b) | (b)if all the associated parking spaces are situated in a covered car park, cable routes for electric vehicle charge points must be installed in— (i)all those associated parking spaces, where there are fewer parking spaces than there are such dwellings with associated parking; or (ii)the number of those associated parking spaces that corresponds to the total number of such dwellings with associated parking. | [8 empty] | Not started
Regulation 44F. - Application of paragraph S3 of Schedule 1 (residential buildings undergoing major renovation)
R44F | Regulation 44F.-(1) | (1) The requirements of paragraph S3 of Schedule 1 apply to a residential building undergoing major renovation as follows. | [8 empty] | Not started
| 44F (2) | (2) The requirements of paragraph S3 of Schedule 1 apply if— (a)the major renovation involves building work being done which includes work being done to any of the following— (i)a car park that is located within the site boundary of the building, where the nature of the work is such that it would be reasonable to expect that work to include enabling the requirements of paragraph S3 of Schedule 1 to be fulfilled; (ii)the electrical infrastructure of a car park, where the car park is located within the site boundary of the building; (iii)the electrical infrastructure of the building, where a car park is located inside the building; (b)the residential building will have more than 10 associated parking spaces upon completion of that work; (c)subject to paragraph (3), all the required electric vehicle charge points can be accommodated within the incoming electrical supply to the building; (d)the cost of installing all the required electric vehicle charge points and cable routes for electric vehicle charge points does not exceed 7% of the total cost of the major renovation; and (e)the residential building is not one in relation to which paragraph (5) applies. | [8 empty] | Not started
| 44F (3) | (3) If paragraph (2)(a), (b) and (e) applies, but all the required electric vehicle charge points cannot be accommodated within the incoming electrical supply to the building— (a)the requirements of paragraph S3 of Schedule 1 apply in respect of the maximum number of electric vehicle charge points that can be accommodated within the incoming electrical supply to the building; and (b)cable routes for electric vehicle charge points must be installed in all remaining associated parking spaces. | [8 empty] | Not started
| 44F (4) | (4) If the cost of installing the required electric vehicle charge points and cable routes for electric vehicle charge points exceeds 7% of the total cost of the major renovation— (a)the residential building is exempt from the requirement to install any electric vehicle charge point; and (b)cable routes for electric vehicle charge points must be installed in all associated parking spaces, except where the cost of that installation exceeds 7% of the total cost of the major renovation. | [8 empty] | Not started
| 44F (5) | (5) The requirements of paragraph S3 of Schedule 1 do not apply to a residential building which is undergoing major renovation for the principal purpose of improving the fire safety of the external walls or roof of the building. | [8 empty] | Not started
| 44E (6) | (6) If a residential building undergoing major renovation has, or will have more than 10 associated parking spaces— (a)if there are or will be any associated parking spaces situated in a position other than in a covered car park— (i)the requirements of paragraph S3 of Schedule 1 must first be applied in relation to those associated parking spaces; then (ii)cable routes for electric vehicle charge points must be installed in all the associated parking spaces in the covered car park; (b)if all the associated parking spaces are situated in a covered car park, cable routes for electric vehicle charge points must be installed in all the parking spaces in the covered car park | [8 empty] | Not started
Regulation 44G. - Application of paragraph S4 of Schedule 1 (erection of new buildings which are not residential buildings or mixed-use buildings)
R44G | Regulation 44G.-(1) | (1) The requirements of paragraph S4 of Schedule 1 apply to the erection of a new building which is not a residential building or a mixed-use building (“new building”) as follows. | [8 empty] | Not started
| 44G (2) | (2) If such a new building has, or will have, within its site boundary, more than 10 parking spaces— (a)if there are or will be any parking spaces situated in a position other than in a covered car park— (i)the requirements of paragraph S4 of Schedule 1 must first be applied in relation to those parking spaces; then (ii)if the number of parking spaces which are situated in a position other than in a covered car park is insufficient to completely fulfil the requirements of paragraph S4 of Schedule 1, cable routes for electric vehicle charge points must be installed in a sufficient number of parking spaces in the covered car park in order to ensure compliance with the requirements of paragraph S4(b) of Schedule 1; (b)if all the parking spaces are situated in a covered car park, cable routes for electric vehicle charge points must be installed in a minimum of one fifth of the total number of those parking spaces. | [8 empty] | Not started
Regulation 44H. - Application of paragraph S5 of Schedule 1 (buildings undergoing major renovation which are not residential buildings or mixed-use buildings)
R44H | Regulation 44H.-(1) | 1) The requirements of paragraph S5 of Schedule 1 apply to a building undergoing major renovation, which is not a residential building or a mixed-use building, as follows. | [8 empty] | Not started
| 44H (2) | (2) The requirements of paragraph S5 of Schedule 1 apply to such a building if— (a)the major renovation involves building work being done which includes work being done to any of the following— (i)a car park that is located within the site boundary of the building, where the nature of the work is such that it would be reasonable to expect the requirements of paragraph S5 of Schedule 1 to be fulfilled; (ii)the electrical infrastructure of a car park, where the car park is located within the site boundary of the building; (iii)the electrical infrastructure of the building, where a car park is located inside the building; (b)upon completion of that major renovation, the building will have more than 10 parking spaces situated within the site boundary of the building; (c)the cost of installing the required electric vehicle charge point and cable routes for electric vehicle charge points does not exceed 7% of the total cost of the major renovation. | [8 empty] | Not started
| 44H (3) | (3) If the cost of installing the required electric vehicle charge point and cable routes for electric vehicle charge points exceeds 7% of the total cost of the major renovation— (a)such a building is exempt from the requirement to install the electric vehicle charge point; and (b)cable routes for electric vehicle charge points must be installed in a minimum of one fifth of the total number of parking spaces, except where the cost of that installation exceeds 7% of the total cost of the major renovation. | [8 empty] | Not started
| 44H (4) | (4) If such a building has, or will have, within its site boundary, more than 10 parking spaces— (a)if there are or will be any parking spaces situated in a position other than in a covered car park— (i)the requirements of paragraph S5 of Schedule 1 must first be applied in relation to those parking spaces; then (ii)if the number of parking spaces which are situated in a position other than in a covered car park is insufficient to completely fulfil the requirements of paragraph S5 of Schedule 1, cable routes for electric vehicle charge points must be installed in the number of parking spaces in the covered car park in order to ensure compliance with the requirements of paragraph S5(b) of Schedule 1; (b)if all the parking spaces are situated in a covered car park, cable routes for electric vehicle charge points must be installed in a minimum of one fifth of the total number of those parking spaces. | [8 empty] | Not started
Regulation 44I. - Application of paragraph S6 of Schedule 1 (the erection of new mixed-use buildings and mixed-use buildings undergoing major renovation)
R44I | Regulation 44I.-(1) | (1) The requirements of paragraph S6 of Schedule 1 apply to the erection of a new mixed-use building and a mixed-use building undergoing major renovation as follows. | [8 empty] | Not started
| 44I (2) | (2) The requirements of paragraph S6 of Schedule 1 apply if, upon completion, such a mixed-use building will have at least one parking space situated within the site boundary of the building. | [8 empty] | Not started
| 44I (3) | (3) If such a mixed-use building has, or will have, within its site boundary, a covered car park— (a)if there are or will be any parking spaces situated in a position other than in a covered car park— (i)the requirements of paragraph S6 of Schedule 1 must first be applied in relation to those parking spaces; then (ii)if the number of parking spaces, which are situated in a position other than in a covered car park, is insufficient to completely fulfil the requirements of paragraph S6 of Schedule 1, cable routes for electric vehicle charge points must be installed in accordance with— (aa)regulation 44D(4)(a), in relation to the associated parking spaces for one or more dwellings in a new mixed-use building; (bb)regulation 44F(6)(a), in relation to the associated parking spaces for one or more dwellings in a mixed-use building undergoing major renovation; (cc)regulation 44G(2)(a), in relation to the parking spaces for one or more premises that are not dwellings in a new mixed-use building; (dd)regulation 44H(4)(a), in relation to the parking spaces for one or more premises that are not dwellings in a mixed-use building undergoing major renovation; | [8 empty] | Not started
| 44I (4) | (b)if all the parking spaces are situated in a covered car park, cable routes for electric vehicle charge points must be installed in accordance with— (i)regulation 44D(4)(b), in relation to the associated parking spaces for one or more dwellings in a new mixed-use building; (ii)regulation 44F(6)(b), in relation to the associated parking spaces for one or more dwellings in a mixed-use building undergoing major renovation; (iii)regulation 44G(2)(b), in relation to the parking spaces for one or more new premises that are not dwellings in a new mixed-use building; (iv)regulation 44H(4)(b), in relation to the parking spaces for one or more premises that are not dwellings in a mixed-use building undergoing major renovation. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part A
Schedule 1 Part A Structure
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
A1 | A1 Loading | (1) The building shall be constructed so that the combined dead, imposed and wind loads are sustained and transmitted by it to the ground— (a) safely; and (b) without causing such deflection or deformation of any part of the building, or such movement of the ground, as will impair the stability of any part of another building | [8 empty] | Not started
| A1 Loading | (2) In assessing whether a building complies with sub-paragraph (1) regard shall be had to the imposed and wind loads to which it is likely to be subjected in the ordinary course of its use for the purpose for which it is intended. | [8 empty] | Not started
A2 | A2 Ground Movement | The building shall be constructed so that ground movement caused by— (a) swelling, shrinkage or freezing of the subsoil; or (b) land-slip or subsidence (other than subsidence arising from shrinkage), in so far as the risk can be reasonably foreseen, will not impair the stability of any part of the building. | [8 empty] | Not started
A3 | A3 Disproportionate Collapse | The building shall be constructed so that in the event of an accident the building will not suffer collapse to an extent disproportionate to the cause. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part B
Schedule 1 Part B Fire Safety
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
B1 | B1 Means of Warning & Escape | The building shall be designed and constructed so that there are appropriate provisions for the early warning of fire, and appropriate means of escape in case of fire from the building to a place of safety outside the building capable of being safely and effectively used at all material times. Requirement B1 does not apply to any prison provided under section 33 of the Prison Act 1952 (power to provide prisons etc). | [8 empty] | Not started
B2 | B2 Internal Fire Spread (linings) | (1) To inhibit the spread of fire within the building, the internal linings shall— (a) adequately resist the spread of flame over their surfaces; and (b) have, if ignited, either a rate of heat release or a rate of fire growth, which is reasonable in the circumstances. (2) In this paragraph “internal linings” means the materials or products used in lining any partition, wall, ceiling or other internal structure | [8 empty] | Not started
B3 | B3 Internal Fire Spread (structure) | (1) The building shall be designed and constructed so that, in the event of fire, its stability will be maintained for a reasonable period | [8 empty] | Not started
| B3 Internal Fire Spread (structure) | (2) A wall common to two or more buildings shall be designed and constructed so that it adequately resists the spread of fire between those buildings. For the purposes of this sub-paragraph a house in a terrace and a semi-detached house are each to be treated as a separate building. | [8 empty] | Not started
| B3 Internal Fire Spread (structure) | (3) Where reasonably necessary to inhibit the spread of fire within the building, measures shall be taken, to an extent appropriate to the size and intended use of the building, comprising either or both of the following— (a) sub-division of the building with fire-resisting construction; | [8 empty] | Not started
| B3 Internal Fire Spread (structure) | (b) installation of suitable automatic fire suppression systems. Requirement B3(3) does not apply to material alterations to any prison provided under section 33 of the Prison Act 1952. | [8 empty] | Not started
| B3 Internal Fire Spread (structure) | (4) The building shall be designed and constructed so that the unseen spread of fire and smoke within concealed spaces in its structure and fabric is inhibited. | [8 empty] | Not started
B4 | B4 External fire spread | (1) The external walls of the building shall adequately resist the spread of fire over the walls and from one building to another having regard to the height, use and position of the building. | [8 empty] | Not started
| B4 External fire spread | (2) The roof of the building shall adequately resist the spread of fire over the roof and from one building to another, having regard to the use and position of the building. | [8 empty] | Not started
B5 | B5 Access and facilities for the fire service | (1) The building shall be designed and constructed so as to provide reasonable facilities to assist fire fighters in the protection of life. | [8 empty] | Not started
| B5 Access and facilities for the fire service | (2) Reasonable provision shall be made within the site of the building to enable fire appliances to gain access to the building. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part C
Schedule 1 Part C Site Preparation and Resistance to Contaminants and Moisture
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
C1 | C1 Preparation of site and resistance to contaminants | (1) The ground to be covered by the building shall be reasonably free from any material that might damage the building or affect its stability, including vegetable matter, topsoil and pre-existing foundations. | [8 empty] | Not started
| C1 Preparation of site and resistance to contaminants | (2) Reasonable precautions shall be taken to avoid danger to health and safety caused by contaminants on or in the ground covered, or to be covered by the building and any land associated with the building. | [8 empty] | Not started
| C1 Preparation of site and resistance to contaminants | (3) Adequate sub-soil drainage shall be provided, if it is needed to avoid— (a) the passage of ground moisture to the interior of the building; (b) damage to the building, including damage through the transport of water-borne contaminants to the foundations of the building. (4) For the purposes of this requirement, “contaminant” means any substance which is or may become harmful to persons or buildings including substances which are corrosive, explosive flammable, radioactive or toxic | [8 empty] | Not started
C2 | C2 Resistance to moisture | The walls, floors and roof of the building shall adequately protect the building and people who use the building from harmful effects caused by— (a) ground moisture; | [8 empty] | Not started
|  | (b) precipitation including wind-driven spray; | [8 empty] | Not started
|  | (c) interstitial and surface condensation; and | [8 empty] | Not started
|  | (d) spillage of water from or associated with sanitary fittings or fixed appliances. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part D
Schedule 1 Part D Toxic Substances
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
D1 | D1 Cavity insulation | If insulating material is inserted into a cavity in a cavity wall, reasonable precautions shall be taken to prevent the subsequent permeation of any toxic fumes from that material into any part of the building occupied by people. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part E
Schedule 1 Part E Resistance to the Passage of Sound
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
E1 | E1 Protection against sound from other parts of the building and adjoining buildings | Dwelling-houses, flats and rooms for residential purposes shall be designed and constructed in such a way that they provide reasonable resistance to sound from other parts of the same building and from adjoining buildings. | [8 empty] | Not started
E2 | E2 Protection against sound within a dwelling-house etc | Dwelling-houses, flats and rooms for residential purposes shall be designed and constructed in such a way that— (a) internal walls between a bedroom or a room containing a water closet, and other rooms; and (b) internal floors, provide reasonable resistance to sound. Requirement E2 does not apply to— (a) an internal wall which contains a door; (b) an internal wall which separates an ensuite toilet from the associated bedroom; (c) existing walls and floors in a building which is subject to a material change of use. | [8 empty] | Not started
E3 | E3 Reverberation in common internal parts of buildings containing flats or rooms for residential purposes | The common internal parts of buildings which contain flats or rooms for residential purposes shall be designed and constructed in such a way as to prevent more reverberation around the common parts than is reasonable. Requirement E3 only applies to corridors, stairwells, hallways and entrance halls which give access to the flat or room for residential purposes. | [8 empty] | Not started
E4 | E4 Acoustic conditions in schools | (1) Each room or other space in a school building shall be designed and constructed in such a way that it has the acoustic conditions and the insulation against disturbance by noise appropriate to its intended use. (2) For the purposes of this Part— “school” has the same meaning as in section 4 of the Education Act 1996; and “school building” means any building forming a school or part of a school. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part F
Schedule 1 Part F Ventilation
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
F1 | F1 Means of ventilation | (1) There shall be adequate means of ventilation provided for people in the building. Requirement F1 does not apply to a building or space within a building— (a) into which people do not normally go; (b) which is used solely for storage; or (c) which is a garage used solely in connection with a single dwelling. | [8 empty] | Not started
| F1 Means of ventilation | (2) Fixed systems for mechanical ventilation and any associated controls must be commissioned by testing and adjusting as necessary to secure that the objective referred to in sub-paragraph (1) is met. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part G
Schedule 1 Part G Sanitation, hot water safety and water efficiency
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
G1 | G1 Cold water supply | (1) There must be a suitable installation for the provision of— (a) wholesome water to any place where drinking water is drawn off; | [8 empty] | Not started
|  | (b) wholesome water or softened wholesome water to any washbasin or bidet provided in or adjacent to a room containing a sanitary convenience; | [8 empty] | Not started
|  | (c) wholesome water or softened wholesome water to any washbasin, bidet, fixed bath and shower in a bathroom; | [8 empty] | Not started
|  | (d) wholesome water to any sink provided in any area where food is prepared. | [8 empty] | Not started
|  | (2) There must be a suitable installation for the provision of water of suitable quality to any sanitary convenience fitted with a flushing device. | [8 empty] | Not started
G2 | G2 Water efficiency | Reasonable provision must be made by the installation of fittings and fixed appliances that use water efficiently for the prevention of undue consumption of water. Requirement G2 applies only when a dwelling is— (a) erected; or (b) formed by a material change of use of a building within the meaning of regulation 5(a) or (b). | [8 empty] | Not started
G2A | G2A Water efficiency of new buildings other than dwellings and healthcare buildings | Reasonable provision must be made in the design and installation of any sanitary convenience, washbasin or shower so as to prevent the undue consumption of water. Requirement G2A applies only to building work that consists of the erection or extension of a building which is not a dwelling or a healthcare building. | [8 empty] | Not started
G3 | Hot water supply and systems | (1) There must be a suitable installation for the provision of heated wholesome water or heated softened water to— (a) any washbasin or bidet provided in or adjacent to a room containing a sanitary convenience; (b) any washbasin, bidet, fixed bath and shower in a bathroom; and (c) any sink provided in any area where food is prepared. | [8 empty] | Not started
|  | (2) A hot water system, including any cistern or other vessel that supplies water to or receives expansion water from a hot water system, must be designed, constructed and installed so as to resist the effects of temperature and pressure that may occur either in normal use or in the event of such malfunctions as may reasonably be anticipated, and must be adequately supported. | [8 empty] | Not started
|  | (3) A hot water system that has a hot water storage vessel must incorporate precautions to— (a) prevent the temperature of the water stored in the vessel at any time exceeding 100°C; (b) ensure that any discharge from safety devices is safely conveyed to where it is visible but will not cause a danger to persons in or about the building. Requirement G3(3) does not apply to a system which heats or stores water for the purposes only of an industrial process. | [8 empty] | Not started
|  | (4) The hot water supply to any fixed bath must be so designed and installed as to incorporate measures to ensure that the temperature of the water than can be delivered to that bath does not exceed 48°C. Requirement G3(4) applies only when a dwelling is— (a) erected; or (b) formed by a material change of use of a building within the meaning of regulation 5(a) or (b). | [8 empty] | Not started
G4 | G4 Sanitary conveniences and washing facilities | (1) Adequate and suitable sanitary conveniences must be provided in rooms provided to accommodate them or in bathrooms. | [8 empty] | Not started
|  | (2) Adequate hand washing facilities must be provided in— (a) rooms containing sanitary conveniences; or (b) rooms or spaces adjacent to rooms containing sanitary conveniences. | [8 empty] | Not started
|  | (3) Any room containing a sanitary convenience, a bidet, or any facility for washing hands provided in accordance with sub-paragraph (2)(b), must be separated from any kitchen or any area where food is prepared. | [8 empty] | Not started
G5 | G5 Bathrooms | A bathroom must be provided containing a washbasin and either a fixed bath or a shower. Requirement G5 applies only to dwellings and to buildings containing one or more rooms for residential purposes. | [8 empty] | Not started
G6 | G6 Kitchens and food preparation areas | A suitable sink must be provided in any area where food is prepared. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part H
Schedule 1 Part H Drainage and waste disposal
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
H1 | H1 Foul water drainage | (1) An adequate system of drainage shall be provided to carry foul water from appliances within the building to one of the following, listed in order of priority— (a) a public sewer; or where that is not reasonably practicable, (b) a private sewer communicating with a public sewer; or where that is not reasonably practicable, (c) either a septic tank which has an appropriate form of secondary treatment or another wastewater treatment system; or, where that is not reasonably practicable, (d) a cesspool. | [8 empty] | Not started
|  | (2) In this Part “foul water” means waste water which comprises or includes— (a) waste from a sanitary convenience, bidet or appliance used for washing receptacles for foul waste; or (b) water which has been used for food preparation, cooking or washing. Requirement H1 does not apply to the diversion of water which has been used for personal washing or for the washing of clothes, linen or other articles to collection systems for reuse. | [8 empty] | Not started
H2 | H2 Wastewater treatment systems and cesspools | (1) Any septic tank and its form of secondary treatment, other wastewater treatment system or cesspool, shall be so sited and constructed that— (a) it is not prejudicial to the health of any person; (b) it will not contaminate any watercourse, underground water or water supply; (c) there are adequate means of access for emptying and maintenance; and (d) where relevant, it will function to a sufficient standard for the protection of health in the event of a power failure | [8 empty] | Not started
|  | (2) Any septic tank or holding tank which is part of a wastewater treatment system or cesspool shall be— (a) of adequate capacity; (b) so constructed that it is impermeable to liquids; and (c) adequately ventilated. | [8 empty] | Not started
|  | (3) Where a foul water drainage system from a building discharges to a septic tank, wastewater treatment system or cesspool, a durable notice shall be affixed in a suitable place in the building containing information on any continuing maintenance required to avoid risks to health. | [8 empty] | Not started
H3 | H3 Rainwater drainage | (1) Adequate provision shall be made for rainwater to be carried from the roof of the building. | [8 empty] | Not started
|  | (2) Paved areas around the building shall be so constructed as to be adequately drained. Requirement H3(2) applies only to paved areas— (a) which provide access to the building pursuant to requirement M1 (access and use), or M1 (access to and use of buildings other than dwellings), requirement M2 (access to extensions to buildings other than dwellings), or requirement M4(1), (2) or (3) (access to and use of dwellings); (b) which provide access to or from a place of storage pursuant to requirement H6(2) (solid waste storage); or (c) in any passage giving access to the building, where this is intended to be used in common by the occupiers of one or more other buildings | [8 empty] | Not started
|  | (3) Rainwater from a system provided pursuant to sub-paragraphs (1) or (2) shall discharge to one of the following, listed in order of priority— (a) an adequate soakaway or some other adequate infiltration system; or, where that is not reasonably practicable, (b) a watercourse; or, where that is not reasonably practicable, (c) a sewer. Requirement H3(3) does not apply to the gathering of rainwater for reuse. | [8 empty] | Not started
H4 | H4 Building over sewers | (1) The erection or extension of a building or work involving the underpinning of a building shall be carried out in a way that is not detrimental to the building or building extension or to the continued maintenance of the drain, sewer or disposal main. | [8 empty] | Not started
|  | (2) In this paragraph “disposal main” means any pipe, tunnel or conduit used for the conveyance of effluent to or from a sewage disposal works, which is not a public sewer. | [8 empty] | Not started
|  | (3) In this paragraph and paragraph H5 “map of sewers” means any records kept by a sewerage undertaker under section 199 of the Water Industry Act 1991. Requirement H4 applies only to work carried out— (a) over a drain, sewer or disposal main which is shown on any map of sewers; or (b) on any site or in such a manner as may result in interference with the use of, or obstruction of the access of any person to, any drain, sewer or disposal main which is shown on any map of sewers. | [8 empty] | Not started
H5 | H5 Separate systems of drainage | Any system for discharging water to a sewer which is provided pursuant to paragraph H3 shall be separate from that provided for the conveyance of foul water from the building. | [8 empty] | Not started
H6 | H6 Solid waste storages | (1) Adequate provision shall be made for storage of solid waste. | [8 empty] | Not started
|  | (2) Adequate means of access shall be provided— (a) for people in the building to the place of storage; and (b) from the place of storage to a collection point (where one has been specified by the waste collection authority under section 46 (household waste) or section 47 (commercial waste) of the Environmental Protection Act 1990) or to a street (where no collection point has been specified). | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part J
Schedule 1 Part J Combustion appliances and fuel storage systems
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
J1 | J1 Air supply | Combustion appliances shall be so installed that there is an adequate supply of air to them for combustion, to prevent over-heating and for the efficient working of any flue. Requirements J1 and J2 apply only to fixed combustion appliances (including incinerators). | [8 empty] | Not started
J2 | J2 Discharge of products of combustion | Combustion appliances shall have adequate provision for the discharge of products of combustion to the outside air. | [8 empty] | Not started
J3 | J3 Warning of release of carbon monoxide | Where a combustion appliance is provided, appropriate provision having regard to the design and location of the appliance shall be made to detect and give early warning of the release of carbon monoxide at levels harmful to persons. Requirement J3 applies only to fixed combustion appliances located in dwellings. | [8 empty] | Not started
J4 | J4 Protection of building | Combustion appliances and flue-pipes shall be so installed, and fireplaces and chimneys shall be so constructed and installed, as to reduce to a reasonable level the risk of people suffering burns or the building catching fire in consequence of their use. Requirement J4 applies only to fixed combustion appliances (including incinerators). | [8 empty] | Not started
J5 | J5 Provision of information | Where a hearth, fireplace, flue or chimney is provided or extended, a durable notice containing information on the performance capabilities of the hearth, fireplace, flue or chimney shall be affixed in a suitable place in the building for the purpose of enabling combustion appliances to be safely installed. | [8 empty] | Not started
J6 | J6 Protection of liquid fuel storage systems | Liquid fuel storage systems and the pipes connecting them to combustion appliances shall be so constructed and separated from buildings and the boundary of the premises as to reduce to a reasonable level the risk of the fuel igniting in the event of fire in adjacent buildings or premises. Requirement J6 applies only to— (a) fixed oil storage tanks with capacities greater than 90 litres and connecting pipes; and (b) fixed liquefied petroleum gas storage installations with capacities greater than 150 litres and connecting pipes, which are located outside the building and which serve fixed combustion appliances (including incinerators) in the building. | [8 empty] | Not started
J7 | J7 Protection against pollution | Oil storage tanks and the pipes connecting them to combustion appliances shall— (a) be so constructed and protected as to reduce to a reasonable level the risk of the oil escaping and causing pollution; and (b) have affixed in a prominent position a durable notice containing information on how to respond to an oil escape so as to reduce to a reasonable level the risk of pollution. Requirement J7 applies only to fixed oil storage tanks with capacities of 3,500 litres or less, and connecting pipes, which are— (a) located outside the building; and (b) serve fixed combustion appliances (including incinerators) in a building used wholly or mainly as a private dwelling, but does not apply to buried systems. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part K
Schedule 1 Part K Protection from falling, collision and impact
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
K1 | K1 Stairs, ladders and ramps | Stairs, ladders and ramps shall be so designed, constructed and installed as to be safe for people moving between different levels in or about the building. Requirement K1 applies only to stairs, ladders and ramps which form part of the building. | [8 empty] | Not started
K2 | K2 Protection from falling | (a) Any stairs, ramps, floors and balconies and any roof to which people have access, and (b) any light well, basement area or similar sunken area connected to a building, shall be provided with barriers where it is necessary to protect people in or about the building from falling. Requirement K2(a) applies only to stairs and ramps which form part of the building. | [8 empty] | Not started
K3 | K3 Vehicle barriers and loading bays | (1) Vehicle ramps and any levels in a building to which vehicles have access, shall be provided with barriers where it is necessary to protect people in or about the building. | [8 empty] | Not started
|  | (2) Vehicle loading bays shall be constructed in such a way, or be provided with such features as may be necessary to protect people in them from collision with vehicles. | [8 empty] | Not started
K4 | K4 Protection against impact with glazing | Glazing, with which people are likely to come into contact while moving in or about the building, shall— (a) if broken on impact, break in a way which is unlikely to cause injury; or (b) resist impact without breaking; or (c) be shielded or protected from impact. | [8 empty] | Not started
K5 | K5.1 Protection from collision with open windows etc. | (1) Provision shall be made to prevent people from moving in or about the building from colliding with open windows, skylights or ventilators. Requirement K5.1 does not apply to dwellings. | [8 empty] | Not started
| K5.2 Manifestation of glazing | Transparent glazing with which people are likely to come into contact while moving in and about the building, shall incorporate features which make it apparent. Requirement K5.2 does not apply to dwellings. | [8 empty] | Not started
| K5.3 Safe opening and closing of windows etc. | Windows, skylights and ventilators which can be opened by people in or about the building shall be so constructed or equipped that they may be opened, closed or adjusted safely. Requirement K5.3 does not apply to dwellings. | [8 empty] | Not started
| K5.4 Safe access for cleaning windows etc. | Provision shall be made for any windows, skylights or translucent walls, ceilings or roofs to be safely accessible for cleaning. (b) Requirement K5.4 does not apply to— (a) dwellings, or (b) any transparent or translucent elements whose surfaces are not intended to be cleaned. | [8 empty] | Not started
K6 | K6 Protection against impact from trapping by doors. | (1) Provision shall be made to prevent any door or gate— (a) which slides or opens upwards, from falling onto any person; and (b) which is powered, from trapping any person. | [8 empty] | Not started
|  | (2) Provision shall be made for powered doors and gates to be opened in the event of a power failure. | [8 empty] | Not started
|  | (3) Provision shall be made to ensure a clear view of the space on either side of a swing door or gate. Requirement K6 does not apply to— (a) dwellings, or (b) any door or gate which is part of a lift | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part L
Schedule 1 Part L Conservation of fuel and power
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
L1 | L1 Conservation of fuel and power | Reasonable provision shall be made for the conservation of fuel and power in buildings by— (a) limiting heat gains and loses— (i) through thermal elements and other parts of the building fabric; and | [8 empty] | Not started
|  | (ii) from pipes, ducts and vessels used for space heating, space cooling and hot water services; | [8 empty] | Not started
|  | (b) providing fixed building services which— (i) are energy efficient to a reasonable standard; (ii) have effective controls; and (iii) are commissioned by testing and adjusting as necessary to ensure they use no more fuel and power than is reasonable in the circumstances. | [8 empty] | Not started
L2 | L2 On-site generation of electricity | Where a system for on-site electricity generation is installed— (a) reasonable provision must be made to ensure that— (i) the system and its electrical output are appropriately sized for the site and available infrastructure; (ii) the system has effective controls; and (b) it must be commissioned by testing and adjusting as necessary to ensure that it produces the maximum electricity that is reasonable in the circumstances | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part M
Schedule 1 Part M Access to and use of buildings
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
M1 | M1 Access to and use of buildings other than dwellings | Reasonable provision must be made for people to— (a) gain access to; and (b) use, the building and its facilities. Requirement M1 does not apply to any part of a building that is used solely to enable the building or any service or fitting in the building to be inspected, repaired or maintained. | [8 empty] | Not started
M2 | M2 Access to extensions to buildings other than dwellings | Suitable independent access must be provided to the extension where reasonably practicable. Requirement M2 does not apply where suitable access to the extension is provided through the building that is extended. | [8 empty] | Not started
M3 | M3 Sanitary conveniences in extensions to buildings other than dwellings | If sanitary conveniences are provided in any building that is to be extended, reasonable provision shall be made within the extension for sanitary conveniences. Requirement M3 does not apply where there is reasonable provision for sanitary conveniences elsewhere in the building, such that people occupied in, or otherwise having occasion to enter the extension, can gain access to and use those sanitary conveniences. | [8 empty] | Not started
M4 | M4(1) Access to and use of dwellings Category 1- visitable dwelling | Reasonable provision must be made for people to— (a) gain access to; and (b) use, the dwelling and its facilities Requirement M4(1) does not apply to: (a) an extension to a dwelling; or (b) any part of a building that is used solely to enable the building or any service or fitting in the building to be inspected, repaired or maintained. | [8 empty] | Not started
| M4(2) optional requirement Category 2- accessible and adaptable dwellings | (1) Reasonable provision must be made for people to— (a) gain access to; and (b) use, the dwelling and its facilities. (2) The provision made must be sufficient to— (a) meet the needs of occupants with differing needs, including some older or disabled people; and (b) to allow adaptation of the dwelling to meet the changing needs of occupants over time. Optional requirement M4(2)— (a) may apply only in relation to a dwelling that is erected; (b) will apply in substitution for requirement M4(1); (c) does not apply where optional requirement M4(3) applies; (d) does not apply to any part of a building that is used solely to enable the building or any service or fitting in the building to be inspected, repaired or maintained. | [8 empty] | Not started
| M4(3) optional requirement Category 3- wheelchair user dwellings | (1) Reasonable provision must be made for people to— (a) gain access to; and (b) use, the dwelling and its facilities. (2) The provision made must be sufficient to— (a) allow simple adaptation of the dwelling to meet the needs of occupants who use wheelchairs; or (b) meet the needs of occupants who use wheelchairs. Optional requirement M4(3)— (a) may apply only in relation to a dwelling that is erected; (b) will apply in substitution for requirement M4(1); (c) does not apply where optional requirement M4(2) applies; (d) does not apply to any part of a building that is used solely to enable the building or any service or fitting in the building to be inspected, repaired or maintained. Optional requirement M4(3)(2)(b) applies only where the planning permission under which the building work is carried out specifies that it shall be complied with. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part O
Schedule 1 Part O Overheating
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
O1 | O1 Overheating mitigation | (1) Reasonable provision must be made in respect of a dwelling, institution or any other building containing one or more rooms for residential purposes, other than a room in a hotel (“residences”) to— (a) limit unwanted solar gains in summer; | [8 empty] | Not started
|  | (b) provide an adequate means to remove heat from the indoor environment. | [8 empty] | Not started
|  | (2) In meeting the obligations in paragraph (1)— (a) account must be taken of the safety of any occupant, and their reasonable enjoyment of the residence; and (b) mechanical cooling may only be used where insufficient heat is capable of being removed from the indoor environment without it. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part P
Schedule 1 Part P Electrical safety
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
P1 | P1 Design and installation | Reasonable provision shall be made in the design and installation of electrical installations in order to protect persons operating, maintaining or altering the installations from fire or injury. The requirements of this Part apply only to electrical installations that are intended to operate at low or extra-low voltage and are— (a) in or attached to a dwelling; (b) in the common parts of a building serving one or more dwellings, but excluding power supplies to lifts; (c) in a building that receives its electricity from a source located within or shared with a dwelling; or (d) in a garden or in or on land associated with a building where the electricity is from a source located within or shared with a dwelling. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part Q
Schedule 1 Part Q Security
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
Q1 | Q1 Unauthorised access | Reasonable provision must be made to deter and] resist unauthorised access to— (a) any dwelling; and (b) any part of a building from which access can be gained to a flat within the building. Requirement Q1 applies only in relation to new dwellings.Requirement Q1 applies only when a dwelling is erected. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part R
Schedule 1 Part R Physical infrastructure for electronic communications
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
RA1 | RA1 Gigabit-ready physical infrastructure | (1) ) Building work must be carried out so as to ensure that each dwelling is equipped with gigabit-ready physical infrastructure that extends from a network termination point for gigabit-capable public electronic communications networks and reaches— (a) a distribution point, or (b) where the person carrying out the building work (“the developer”) has no right to install gigabitready physical infrastructure in land in which it would have to be installed if it were to reach a distribution point, as close as is reasonably practicable to a distribution point, or | [8 empty] | Not started
|  | (c) where the developer has no such right and requirement RA2 is excluded or modified by regulation 44ZC, and would be so excluded or modified even if the gigabit-ready physical infrastructure were required to reach as close as is reasonably practicable to a distribution point— (i) as close as is reasonably practicable to a location at which a distribution point is likely to be installed within the relevant 2-year period (a “likely future location”), or (ii) where there is no likely future location that is closer to the building than the closest distribution point already installed, an access point for gigabit-capable public electronic communications networks, or | [8 empty] | Not started
|  | (d) where the developer has no right to install gigabit-ready physical infrastructure in land beyond the building, an access point for gigabitcapable public electronic communications networks. | [8 empty] | Not started
|  | (2) Where the work concerns a building containing more than one dwelling, the work must be carried out so as to ensure that the building is equipped in addition with a common access point for gigabit-capable public electronic communications networks. (3) In this paragraph— “distribution point” means a distribution point for a gigabit-capable public electronic communications network; “the relevant 2-year period” means the period of 2 years beginning with the earlier of the following— (a) the day on which a building notice, initial notice or public body’s notice relating to work to which this paragraph applies is given; (b) he day on which an application for building control approval with full plans relating to building work to which this paragraph applies is given. Requirements RA1 and RA2 apply to the erection of a dwelling or of a building that contains one or more dwellings. Refer also to Regulation 44ZC | [8 empty] | Not started
RA2 | RA2 Connection to gigabit-capable network | Each dwelling must in addition be provided with a connection to a gigabit-capable public electronic communications network. Requirements RA1 and RA2 apply to the erection of a dwelling or of a building that contains one or more dwellings. | [8 empty] | Not started
R1 | R1 High-speed ready in-building physical infrastructure | (1) Building work must be carried out so as to ensure that the building is equipped with a high-speed ready in-building physical infrastructure, up to a network termination point for high-speed electronic communications networks. (2) Where the work concerns a building containing more than one dwelling, the work must be carried out so as ensure that the building is equipped in addition with a common access point for high-speed electronic communications networks. Requirement R1 applies, other than building work to which paragraph RA1 applies, to building work that consists of— (a) the erection of a building; or (b) major renovation works to a building | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part S
Schedule 1 Part S Infrastructure for the charging of electric vehicles (refer to Part 9B for application)
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
S1 | S1 The erection of new residential buildings | (1) A new residential building with associated parking must have access to electric vehicle charge points as provided for in paragraph (2). (2) The number of associated parking spaces which have access to electric vehicle charge points must be— (a) the total number of associated parking spaces, where there are fewer associated parking spaces than there are dwellings contained in the residential building; or (b) the number of associated parking spaces that is equal to the total number of dwellings contained in the residential building, where there are the same number of associated parking spaces as, or more associated parking spaces than, there are dwellings. | [8 empty] | Not started
|  | (3) Cable routes for electric vehicle charge points must be installed in any associated parking spaces which do not, in accordance with paragraph (2), have an electric vehicle charge point where— (a) a new residential building has more than 10 associated parking spaces; and (b) there are more associated parking spaces than there are dwellings contained in the residential building. | [8 empty] | Not started
S2 | S2 Dwellings resulting from a material change of use | Where one or more dwellings with associated parking result from a building, or a part of a building, undergoing a material change of use at least one associated parking space for the use of each such dwelling must have access to an electric vehicle charge point. | [8 empty] | Not started
S3 | S3 Residential buildings undergoing major renovation | Where a residential building undergoing major renovation will have more than 10 associated parking spaces after the major renovation is completed— (a) at least one associated parking space for the use of each dwelling must have access to an electric vehicle charge point; (b) cable routes for electric vehicle charge points must be installed in all additional associated parking spaces. | [8 empty] | Not started
S4 | S4 Erection of new buildings which are not residential buildings or mixed-use buildings | Where a new building which is not a residential building or a mixed-use building has more than 10 parking spaces— (a) one of those parking spaces must have access to one electric vehicle charge point; and (b) cable routes for electric vehicle charge points must be installed in a minimum of one fifth of the total number of remaining parking spaces. | [8 empty] | Not started
S5 | S5 Buildings undergoing major renovation which are not residential buildings or mixed-use buildings | Where a building undergoing major renovation, which is not a residential building or a mixed-use building, will have more than 10 parking spaces after the major renovation is completed— (a) one of those parking spaces must have access to one electric vehicle charge point; and (b) cable routes for electric vehicle charge points must be installed in a minimum of one fifth of the total number of remaining parking spaces. | [8 empty] | Not started
S6 | S6 The erection of new mixed-use buildings and mixed-use buildings undergoing major renovation | (1) The requirements of paragraph S1 apply in respect of the part of the new mixed-use building that contains one or more dwellings and the associated parking spaces that are assigned to those dwellings. (2) The requirements of paragraph S3 apply in respect of the part of the mixed-use building that is undergoing major renovation that contains one or more dwellings and the associated parking spaces that are assigned to those dwellings. (3) The requirements of paragraph S4 apply in respect of the part of the new mixed-use building that contains one or more new premises that are not dwellings and the parking spaces that are assigned to those premises. (4) The requirements of paragraph S5 apply in respect of the part of the mixed-use building that is undergoing major renovation that contains one or more premises that are not dwellings and the parking spaces that are assigned to those premises. | [8 empty] | Not started
Version 2024.08 - Formatting updated

## Sch.1-Part T
Part T Toilet accommodation
|  | Content in green is deemed relevant to this project. Content shaded grey is not relevant. | Party responsible for meeting functional requirement
Ref | Building Regulation | Functional Requirement Limits on application shown in italics. | Strategy | Stage 2 Concept | Stage 3 Spatial design | Stage 4 Technical design | Route to compliance | Design guidance followed | Design strategy / solution | Notes & Links to evidence | Submission status | Action required | Row last updated
T1 | T1 Toilet accommodation | (1) Toilet accommodation in buildings other than dwellings— (a) must consist of— (i) reasonable provision for male and female single-sex toilets, or (ii) where space precludes provision of single-sex toilets, universal toilets, and (b) may consist of universal toilets in addition to single-sex toilets. (2) In this requirement— “single-sex toilet” means toilet facilities which— (a) are intended for the exclusive use of persons of the same sex, and (b) provide washbasins and hand-drying facilities in— (i) either the toilet room or cubicle, or (ii) a separate area intended for use only by persons of that sex. “universal toilet” means toilet facilities which— (a) are provided in a fully enclosed room which contains a water closet and washbasin and hand-drying facilities, and (b) is intended for individual use by persons of either sex. Requirement T1 does not apply to— (a) en-suite facilities in individual rooms for residential purposes; (b) residential rooms in care homes as defined at section 3 of the Care Standards Act 2000; (c) schools as defined in section 4 of the Education Act 1996; (d) premises, or part of any premises, used wholly or mainly for early years provision within the meaning of section 20 of the Childcare Act 2006 by an early years provider to whom section 40 of the Childcare Act 2006 (Duty to implement Early Years Foundation Stage) applies; (e) cellular accommodation in custodial facilities | [8 empty] | Not started
Version 2024.08 - Formatting updated

## RIBA Version Control
Version | Date Published | Revisions within the version.
V1 | 2024-05-01 | Relevant requirements current at launch, awaiting Part T detail
V2 | 2025-01-01 | Print areas adjusted. Requirement T1 included. Part 9B 44D-44I included. Formatting updated generally to align with key/ charts and 'not relevant' greyed out on selection. Limit in application of H1.1 added. Part K4 updated.