## Monitoring sheet
Current situation summary (from records)
Report date
Stage reached
%age of stage completed
Total fee to date
Budget cost to date
Actual cost to date
Fee billing to completion
Budget cost to completion
Fee budget summary |  | Budget cost | Fee quote | Planned profit
Cost to date
Stage 0/1
Stage 2
Stage 3
Stage 4
Stage 5
Stage 6
Total
Progress summary | Cost to date | %age complete | Fee invoiced | Actual profit
Cost to date |  |  |  | #DIV/0!
Stage 0/1 |  |  |  | #DIV/0!
Stage 2 |  |  |  | #DIV/0!
Stage 3 |  |  |  | #DIV/0!
Stage 4 |  |  |  | #DIV/0!
Stage 5 |  |  |  | #DIV/0!
Stage 6 |  |  |  | #DIV/0!
Total | 0 |  | 0 | #DIV/0!
The cost to date is derived from the timesheet records.

## Worked example
Current situation summary (from records) |  |  | Worked example
Report date |  |  |  | 2013-10-15
Stage reached |  |  |  | 3
%age of stage completed |  |  |  | 50%
Total fee to date |  |  |  | 129201
Budget cost to date |  |  |  | 105377
Actual cost to date |  |  |  | 103694
Fee billing to completion |  |  |  | 534204
Budget cost to completion |  |  |  | 444502
Fee budget summary |  | Budget cost | Fee quote | Planned profit
Cost to date |  | 2250 | 2250 | 0%
Stage 0/1 |  | 32790 | 40988 | 25%
Stage 2 |  | 31162 | 38953 | 25%
Stage 3 |  | 78349 | 94019 | 20%
Stage 4 |  | 201499 | 241799 | 20%
Stage 5 |  | 187772 | 225326 | 20%
Stage 6 |  | 16056 | 20069 | 25%
| Total | 549878 | 663404 | 21%
Progress summary | Cost to date | %age complete | Fee invoiced | Actual profit
Cost to date | 2250 | 100% | 2250 | 0%
Stage 0/1 | 31150 | 100% | 40988 | 32%
Stage 2 | 33140 | 100% | 38953 | 18%
Stage 3 | 37154 | 50% | 47010 | 27%
Stage 4 | 0 | 0% | 0
Stage 5 | 0 | 0% | 0
Stage 6 | 0 | 0% | 0
Total | 103694 |  | 129201
The cost to date is derived from the timesheet records.